## Comment Log
Reviewer To Write | [7 empty] | Author |  |  | Reviewer to Write
Item # | File Name | Page / Slide | Question / Comment | Date | Person | Severity | Comment | Answer | Updated Presentation Slide Number | Status | Status | Completed Date | Date Row Last Updated | Group
1 | App Discovery AIRES v1.3 | 6 | Assessment at a Glance: #2, add date for extended support for SQL Server 2012 | 2019-12-03 | K. Guymon | Low |  |  |  |  | Open |  | 2019-12-03 | AIRES
2 | App Discovery AIRES v1.3 | 6 | Assessment at a Glance: #5, adjust "Not Viable Option … to vNS not currently supported on Azure". Change to indicate Hosting on Azure would require major reengineering/rewrite | 2019-12-03 | K. Guymon | Low |  |  |  |  | Open |  | 2019-12-03 | AIRES
3 | App Discovery AIRES v1.3 | 9 | Manual External Inputs (SP1.4, SP1.11, SP1.5, SP1.7, SP1.9, SP1.10, SP1.8, SP1.12) and Interally Generated Work (SP1.13, SP1.6) it would be benefical to know the source of this information to determine if automation could be added. | 2019-12-03 | K. Guymon | Medium |  | It is our understanding these flows are process inputs manually used to update the Aires application. There may be oppurtuties for automation and we will investigate during design | 9 | Pending | Open |  | 2019-12-03 | AIRES
49 | App Discovery AIRES v1.3 | 9 | CDG client uses https (SOAP) to connect to the NSK (2) | 2019-12-04 | S. Love | low |  |  |  |  | Open |  | 2019-12-04 | AIRES
24 | App Discovery AIRES v1.3 | 11 | Unable to locate definition of downstream interfaces | 2019-12-03 | K. Guymon | High |  | Aires sends text data back to STEPS via SFTP | Bi-directional flow indicated on slide 9 | Closed | Open |  | 2019-12-03 | AIRES
30a | App Discovery AIRES v1.3 | 11 | Interface Information is inaccurate see Finding #30,31,32,33,34,35 | 2019-12-04 | K. Guymon | High |  |  |  |  | Open |  | 2019-12-03 | AIRES
30 | App Discovery AIRES v1.3 | 11 | (line 1) We don't get DIPS files (CALC Master, AIRLINE Master and CONTREV) via ODBC. They get to the NS via SFTP. A process in DIPS generates the files and then APS processing uses SFTP to place the files in the correct location on the Non-Stop. | 2019-12-04 | N. Bartlett | High |  | Changed ODBC to SFTP on slide 11 | 11 | Pending | Open |  | 2019-12-03 | AIRES
31 | App Discovery AIRES v1.3 | 11 | (line 2) There are two interfaces for eMOD. One interface is a SOAP webservice and the other is an XML file that is sent nightly to eMOD via EFDS. | 2019-12-04 | N. Bartlett | High |  | Added Downstream interface for eMOD | 11 | Robert | Open |  | 2019-12-03 | AIRES | Robert to update drawing on slide 9 | Robert to fix slide 11
32 | App Discovery AIRES v1.3 | 11 | (line 3) There are two interface for OneSAP. One interface is a RESTFUL API running on RHEL that utilizes that AIRES SOAP API's. The other is a monthly report that gets sent to OneSAP via EFDS. | 2019-12-04 | N. Bartlett | High |  | Added Downstream interface for OneSAP | 11 | Robert | Open |  | 2019-12-03 | AIRES | Robert to update drawing on slide 9 | Robert to fix slide 11
33 | App Discovery AIRES v1.3 | 11 | (line 4) The CDW XML files are brought into the CDG network via Axway and the SFTP'd onto the Non-Stop | 2019-12-04 | N. Bartlett | Medium |  | Changed ODBC to Axway and SFTP on slide 11 Shannon to confirm w/Nate | 11 | Pending | Open |  | 2019-12-03 | AIRES
34 | App Discovery AIRES v1.3 | 11 | I don't understand the difference betwwen line 1 and line 9. We get three files from DIPS Airline Master, Calc Master and CONTREV. The CONTREV file contains revision schedule information. The Airline Master file contains airline to CALC_NO relationship. The CALC Master contians the CALC to airplane (effectivity) relationship. | 2019-12-04 | N. Bartlett | High |  | Removed line 9. | 11 | Pending | Open |  | 2019-12-03 | AIRES
35 | App Discovery AIRES v1.3 | 11 | (line 10) BCF information is compiled by the user into a spread sheet which is then uploaded into the AIRES UI. The AIRES UI parses the spread sheet and puts the data into a SOAP request. | 2019-12-04 | N. Bartlett | Medium |  | Added information to slide | 11 | Pending | Open |  | 2019-12-03 | AIRES
36a | App Discovery AIRES v1.3 | 12 | As-Is Configuration - Logical View is inaccurate. See Findings #36,37,37,38,50) | 2019-12-04 | K. Guymon | High |  |  |  |  | Open |  | 2019-12-03 | AIRES
36 | App Discovery AIRES v1.3 | 12 | (process flow 1) The nexus services are consumed by the AIRES UI, CNC, OneSAP and OneView (if you consider the OneView Java service a nexus service) | 2019-12-04 | N. Bartlett | High |  | Updated Process Flow | 12 | Pending | Open |  | 2019-12-04 | AIRES
37 | App Discovery AIRES v1.3 | 12 | (process flow 6) OneView is an alternative UI for AIRES that was developed to address certain desires of the Service Bulletin Authoring team. I don't belive there are non-CDG personal that utilize it. | 2019-12-04 | N. Bartlett | High |  | Updated Process Flow | 12 | Pending | Open |  | 2019-12-04 | AIRES
38 | App Discovery AIRES v1.3 | 12 | (process flow 3) Kafka only handles messaging for the Nexus services involved in batch processing (namely the syncing of QD DSI data from STEPS). | 2019-12-04 | N. Bartlett | Medium |  | Fixed process flow on slide | 12 | Pending | Open |  | 2019-12-04 | AIRES
39 | App Discovery AIRES v1.3 | 12 | I don't believe there is any interaction between the AIRES SSRS and the A-Team app serverers. (AIRES SSRS and ATEAM SSRS are separate) | 2019-12-04 | N. Bartlett | High |  | Process flow was recreated from AIRES Topology Drawing provided by CDG. Shannon to confirm w/Nate | 12 | Pending | Open |  | 2019-12-04 | AIRES
50 | App Discovery AIRES v1.3 | 12, 13 | QA HUB is integrating into the AIRES client with 1.143… It uses ODBC to MS sql then LINKED server ODBC to NSK | 2019-12-04 | S. Love | Medium |  |  |  | Robert | Open |  | 2019-12-04 | AIRES | Robert to update drawing on slide 12,13
40a | App Discovery AIRES v1.3 | 13 | As-Is Configuration - Physical View is inaccurate. See Findings #40,41,42,50,51,52,53) | 2019-12-04 | K. Guymon | High |  |  |  |  | Open |  | 2019-12-03 | AIRES
40 | App Discovery AIRES v1.3 | 13 | I'm not aware of any ODBC connection between DIPS and AIRES | 2019-12-04 | N. Bartlett | High |  | This was included in discovery documents for DIPS. Shannon to confirm w/Nate | 13 | Pending | Open |  | 2019-12-04 | AIRES
41 | App Discovery AIRES v1.3 | 13 | PICES pull data from the AIRES SQL/MX database via ODBC. The is no SOAP interface involved. | 2019-12-04 | N. Bartlett | Medium |  |  |  | Robert | Open |  | 2019-12-04 | AIRES | Robert to update drawing on slide 13
42 | App Discovery AIRES v1.3 | 13 | I'm not sure if GEMINI pulls data through ODBC from the AIRES SQL/MX directly or if it uses the MSSQL replicated data. | 2019-12-04 | N. Bartlett | High |  | This was included in discovery documents for GEMINI. Shannon to confirm w/Nate | 13 | Pending | Open |  | 2019-12-04 | AIRES
51 | App Discovery AIRES v1.3 | 13 | AIRES SSRS server uses Restful API call and Filestream (IP protocol) to Gemini web server and image repository | 2019-12-04 | S. Love | Medium |  |  |  | Robert | Open |  | 2019-12-04 | AIRES | Robert to add line to drawing on slide 13
52 | App Discovery AIRES v1.3 | 13 | Ateam App server uses ODBC to Report (MS SQL) | 2019-12-04 | S. Love | Medium |  |  |  | Robert | Open |  | 2019-12-04 | AIRES | Robert to update drawing on slide 13
53 | App Discovery AIRES v1.3 | 13 | PICE uses ODBC to connect to NSK not SOAP, unless there is more features than I am familiar with… It's correct on page 9. | 2019-12-04 | S. Love | Medium |  | Shannon to confirm |  | Robert | Open |  | 2019-12-04 | AIRES | Robert to update drawing on slide 13
4a | App Discovery AIRES v1.3 | 14,15 | Data Overview (As-Is) - NonStop and Data Overview (As-Is) - SQL Server (See Findings 4,43,55,56) | 2019-12-04 | K. Guymon | High |  |  |  |  | Open |  | 2019-12-03 | AIRES
4 | App Discovery AIRES v1.3 | 14,15 | AIRES has BPI, ITAR, EAR-NLR, EAR-LR, PIO, and potentially PII, PII - Sensentive data Special Data Handling needs to be updated based on InfoTypeByApp data that was provided in Nov (https://collab2.web.boeing.com/sites/OEIAHRestrictedAcces/CDG/Shared Documents/IBM POC/1 - Applications Working Folders/Misc/InfoTypeByApp.xlsx) | 2019-12-03 | K. Guymon | High |  | Updated slide 14, 15 to indicate BPI, ITAR, EAR-NLR, EAR-LR, PIO, and potentially PII, PII - Sensentive data | 14,15 | Pending | Open |  | 2019-12-03 | AIRES
54 | App Discovery AIRES v1.3 | 14 | Is the special data handling correct? We consider it ITAR and EAR restricted. | 2019-12-04 | S. Love | Repeat |  |  |  |  | Closed
43 | App Discovery AIRES v1.3 | 14 | (line 7) the application code isn't resident on the Non-Stop but in bitbucket. The description here is more a continuation of line 6. | 2019-12-04 | N. Bartlett | Medium |  | Removed the word 'Code' from the slide | 14 | Pending | Open |  | 2019-12-04 | AIRES
55 | App Discovery AIRES v1.3 | 15 | line 4 - DR is another available and redundant system, not restored from backup. Only applies to AIRES replicated Data and not ATEAM application databases | 2019-12-04 | S. Love | medium |  | Check w/Nate & Steve | 15 | Pending | Open |  | 2019-12-04 | AIRES
56 | App Discovery AIRES v1.3 | 15 | line 5 - NO Backups of any replicated Data necessary. Source is NSK and restoration must come from NSK. Only applies to AIRES replicated Data and not ATEAM application databases | 2019-12-04 | S. Love | medium |  | Check w/Nate & Steve | 15 | Pending | Open |  | 2019-12-04 | AIRES
57 | App Discovery AIRES v1.3 | 15 | Is the special data handling correct? We consider it ITAR and EAR restricted. | 2019-12-04 | S. Love | Repeat |  |  |  |  | Closed
6a | App Discovery AIRES v1.3 | 17,18 | Bill of Materials (As-Is) See findings (6,58,44,45,59,60) | 2019-12-04 | K. Guymon | High |  |  |  |  | Open |  | 2019-12-03 | AIRES
6 | App Discovery AIRES v1.3 | 17 | Unclear if Sonatype Nexus API, Kafka, STRIIM, Couchbase, Pathsend in future design. If yes, need to verify approved for use. Capture MSR for licensing, and confirm will work with vNS | 2019-12-03 | K. Guymon | High |  | At the time of writing the Assesment; It is assumed that these technologies will be used. However, we will determine more information during the design phase | 17 | Pending | Open |  | 2019-12-04 | AIRES
58 | App Discovery AIRES v1.3 | 17 | line 7 - SSRS, currently windows server 2008 and SQL 2008. Migrating to window server 2016 and sql 2017 by Jan 2020 | 2019-12-04 | S. Love | Medium |  | Added information to slide | 17 | Robert | Open |  | 2019-12-04 | AIRES | Robert to clean up slide
44 | App Discovery AIRES v1.3 | 18 | The AIRES application code is currently version 1.136 and we are looking to deploy 1.143 in December. The AIRES UI code utilizes .NET 4.6.1 . The AIRES Non-Stop code is currently running on L16.05.00 | 2019-12-04 | N. Bartlett | Medium |  | Updated slides. Need UI version from Steve Shannon to talk to Nate/Steve | 18 | Pending | Open |  | 2019-12-04 | AIRES
45 | App Discovery AIRES v1.3 | 18 | We are currently evaluting moving to STRIIM 3.9.6.3 from STRIM 3.7.2D | 2019-12-04 | N. Bartlett | Medium |  | Added Striim version to slide | 18 | Pending | Open |  | 2019-12-04 | AIRES
59 | App Discovery AIRES v1.3 | 18 | Update Comment on Line 1 to include. AIRES application code is complicated and composed of front end and back end. .net framework, JAVA and react/redux required | 2019-12-04 | S. Love | Medium |  | Added comment to slide | 18 | Pending | Open |  | 2019-12-04 | AIRES
60 | App Discovery AIRES v1.3 | 18 | SSRS version moving to 2017 | 2019-12-04 | S. Love | Medium |  | Added comment to slide | 18 | Robert | Open |  | 2019-12-04 | AIRES | Robert to clean up slide
5 | App Discovery AIRES v1.3 | 19 | Add STRIIM as a security consideration and Recommendation/requirement to use GoldenGate | 2019-12-03 | K. Guymon | Medium |  | Added comment to slide | 19 | Pending | Open |  | 2019-12-03 | AIRES
7 | App Discovery AIRES v1.3 | 19 | Unclear why Security Consideration #6 is included. Is there currently external access? If no, this should be removed | 2019-12-03 | K. Guymon | Medium |  | Comment Removed | 19 | Pending | Open |  | 2019-12-03 | AIRES
46 | App Discovery AIRES v1.3 | 20,22,34 | There is no AIRES code in SVN | 2019-12-04 | N. Bartlett | High |  | Removed reference to SVN | 17 | Pending | Open |  | 2019-12-04 | AIRES
47 | App Discovery AIRES v1.3 | 22 | This slide is might be correct for the C# UI code, but not for the Non-Stop Code | 2019-12-04 | N. Bartlett | High |  | Modified Slide to show correct repositories Shannon to confirm w/Nate | 22 | Pending | Open |  | 2019-12-04 | AIRES
8 | App Discovery AIRES v1.3 | 27 | Should we consider altering this slightly to have DR equip move to Boeing Data Center which might be less disruptive. | 2019-12-03 | K. Guymon | Medium |  |  |  |  | Defer to Design |  | 2019-12-03 | AIRES
9 | App Discovery AIRES v1.3 | 27 | missing logical grouping requirements (association to other applications) | 2019-12-03 | K. Guymon | High |  |  |  |  | Defer to Design |  | 2019-12-03 | AIRES
10 | App Discovery AIRES v1.3 | 27 | We need to explore Option #2 in greater depth; including the specific plans and timeline for AIRES as described by 2CES Team | 2019-12-03 | K. Guymon | High |  |  |  |  | Defer to Design |  | 2019-12-03 | AIRES
11 | App Discovery AIRES v1.3 | 27 | Option 1: need to clarify what would be put in Azure Gov vs Boeing Enterprise "AIRES Sytems outside of NonStop will be migrated to BEN or Azure" | 2019-12-03 | K. Guymon | High |  |  |  |  | Defer to Design |  | 2019-12-03 | AIRES
11 | App Discovery AIRES v1.3 | 27 | Option 1: Benefits / Pros " Most expeditious path to migrate by YE 2020", Unclear why this would be faster than Option 3 | 2019-12-03 | K. Guymon | Medium |  |  |  |  | Defer to Design |  | 2019-12-03 | AIRES
12 | App Discovery AIRES v1.3 | 28 | Boeing Team needs to adjust costs depicted on BOM MSRP for: 1. HP Discount 2. Credit NSK to VNS | 2019-12-03 | K. Guymon | High |  |  |  |  | Defer to Design |  | 2019-12-03 | AIRES
13 | App Discovery AIRES v1.3 | 29 | SSRS - Costs is already in ATEAM right? Understand there is an SSRS service for AIRES, but think this is part of overall SSRS app | 2019-12-03 | K. Guymon | Medium |  |  |  |  | Defer to Design |  | 2019-12-03 | AIRES
14 | App Discovery AIRES v1.3 | 29 | Design is not clear enough to interpret BOM | 2019-12-03 | K. Guymon | High |  |  |  |  | Defer to Design |  | 2019-12-03 | AIRES
26 | App Discovery AIRES v1.3 | 29 | STRIIM is referenced in cost estimates but called out previously as non-standard and need to use Golden Gate | 2019-12-03 | K. Guymon | High |  |  |  |  | Defer to Design |  | 2019-12-03 | AIRES
| App Discovery AIRES v1.3 | 30 | Additional option to establish expand line through VPN to Boeing datacenter and engage RDF replication to new system. Advantage is Zero downtime. | 2019-12-04 | S. Love | n/a |  |  |  |  | Defer to Design |  | 2019-12-04 | AIRES
19 | App Discovery AIRES v1.3 | 36 | Risk #1: Consequence of Risk is shown as a Low (2), however without the vNS the entire Option / Recommendation will not work. Therefore Consequence seems more like High (5) | 2019-12-03 | K. Guymon | Medium |  |  |  |  | Defer to Design |  | 2019-12-03 | AIRES
20 | App Discovery AIRES v1.3 | 36 | Risk #2: Unclear. Slide 30, and Slide 33 both outline transfer protocols. Clarify risk, Impact | 2019-12-03 | K. Guymon | Medium |  |  |  |  | Defer to Design |  | 2019-12-03 | AIRES
21 | App Discovery AIRES v1.3 | 36 | Risk #3: Kernel changes needs to much more clearly defined. * Why Required * What will change * Support Impact * Upgrade Impact * Security Considerations | 2019-12-03 | K. Guymon | High |  |  |  |  | Defer to Design |  | 2019-12-03 | AIRES
48 | App Discovery AIRES v1.3 | 36 | Any Kernal changes for vNS has already been made by HP. IBM will not need to modify the HP Non-Stop OS. In our POC testing we didn't see anything that indicated a physical Non-Stop dependancy. Getting our code to build on vNS only required minor changes in the options passed to the linker during compilation. | 2019-12-04 | N. Bartlett | High |  |  |  |  | Defer to Design |  | 2019-12-04 | AIRES
22 | App Discovery AIRES v1.3 | 36 | Risk #4: Spelling error (Rick vs Risk) | 2019-12-03 | K. Guymon | Low |  |  |  |  | Defer to Design |  | 2019-12-03 | AIRES
23 | App Discovery AIRES v1.3 | 36 | Risk #4: Risk basically stating that tight Coupling = Must migrate simultaneously. The Risk needs to be clarified…are they really required to migrate simulatenously? What happens (Impact) if they do not migrate simulteanously? Additionally, mitigation is weak and doesn't appear to address requirement (simultaneous migration). | 2019-12-03 | K. Guymon | High |  |  |  |  | Defer to Design |  | 2019-12-03 | AIRES
25 | App Discovery AIRES v1.3 | 40 | Missing Reference location of files and configuration control for Files mentioned on Reference Sheet | 2019-12-03 | K. Guymon | Medium |  |  |  |  | Defer to Design |  | 2019-12-03 | AIRES
16 | App Discovery AIRES v1.3 | 27, 30 | Need to determine if architecture which sends APIs / Messaging thru Cloud (NEXUS, Couchbase, Kafka, STRIIM…) is the most cost effective and specific benefits which Cloud Hosting would provide over hosting Boeing Enterprise | 2019-12-03 | K. Guymon | High |  |  |  |  | Defer to Design |  | 2019-12-03 | AIRES
17 | App Discovery AIRES v1.3 | 27, 30 | Need to determine if architecture which sends APIs / Messaging thru Cloud (NEXUS, Couchbase, Kafka, STRIIM…) is the most cost effective and specific benefits which Cloud Hosting would provide over hosting Boeing Enterprise | 2019-12-03 | K. Guymon | High |  |  |  |  | Defer to Design |  | 2019-12-03 | AIRES
15 | App Discovery AIRES v1.3 | 27,30 | Continuity needs further refinement and clarification to fully understand approach ("...Affinitity with PICES, DIPS, GEMINI, Legacy Pub ...IBM is exploring options to separate these environments") | 2019-12-03 | K. Guymon | Medium |  |  |  |  | Defer to Design |  | 2019-12-03 | AIRES
61 | App Discovery AIRES v1.3 | 28, 29 | Is the Development system included in DR? seems light when we count AIRES and ATEAM dev. | 2019-12-04 | S. Love | Medium |  |  |  |  | Defer to Design |  | 2019-12-04 | AIRES
18 | App Discovery AIRES v1.3 | 30, 33 | Migration Continuity approach and Additional Comments Considerations (data volumes) seem out of sync. Slide 30 bullet #4 is calling out 3 options, whereas slide 33 is specifying use of MFT and giving data transfer timing. | 2019-12-03 | K. Guymon | Medium |  |  |  |  | Defer to Design |  | 2019-12-03 | AIRES
27 | All Deliverables | Overall | Options Analysis is too generic. It lacks sufficient details that would enable understanding of the options. missing clear enumeration of Technical Proposals, impact to ecosystem, costs, duration, and sufficient comparison between options. | 2019-12-03 | K. Guymon | High |  |  |  |  | Defer to Design |  | 2019-12-03 | All
28 | All Deliverables | Overall | Wave Plan (Phasing) needs to be aligned with Options and any Event Fabric proposals | 2019-12-03 | K. Guymon | High |  |  |  |  | Defer to Design |  | 2019-12-03 | All
29 | All Deliverables | Overall | Technical Proposal / Options need to provide clear picture of proposal (Options) for applications; including targeted environment, migration strategy, migration complexity. Improve Technical View /Clarity – Ecosystem / System of Systems with relationship to Event Fabric and the in-scope application. | 2019-12-03 | K. Guymon | High |  |  |  |  | Defer to Design |  | 2019-12-03 | All
Note on G2: High : Major Flaw or Omission Middle: Error that impacts understanding, execution Low : Grammatical or context error that does not hamper understanding
Note on L2: Open Pending Closed Cancel

## Sheet1
Status Pick List
Open
Need to Discuss
Ready for Review
Closed
Defer to Design

## PivotBySeverityAndStatus
Count of Item # | Column Labels
Row Labels | Open | Defer to Design | Closed | Grand Total
High | 19 | 14 |  | 33
Medium | 19 | 9 |  | 28
Low | 3 | 1 |  | 4
Repeat |  |  | 2 | 2
n/a
Grand Total | 41 | 24 | 2 | 67