## Comment Log
Reviewer To Write | [7 empty] | Author |  |  |  | Reviewer/Author | Reviewer to Write
Item # | File Name | Page / Slide | Question / Comment | Date | Person | Severity | Comment | Accepted by IBM | Answer | Updated Presentation Slide Number | Status | Status | Completed Date | Date Row Last Updated | Group | Application
xxx | App Discovery - CG System v1.3 | 5 | Assessment at a Glance #3 - states "Authentication to app… May be issue with Boeing Security". Clarify why this is an issue | 2019-12-10 | K. Guymon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CG System
xxx | App Discovery - CG System v1.3 | 6 | Interfaces flow into and out of an aggregrate Application Set (HP Non-Stop Authoring) on the dagram, this makes it more difficult to understand | 2019-12-10 | K. Guymon | Low | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CG System
1 | App Discovery - CG System v1.3 | 8 | Flow order seems a bit odd - Is DSI data be sent before (or after) users do their value-added work in CG system? (As written, it indicates before). Flow should reflect data sent at end of revision 12/9/19 (EEN): The data is sent at the end of a revision - after the users do their value added work. Process Flow is reflected accurately on slide 9 12/10/19 (KRG): Numbers are not intended to reflect flow order, rather reference points on the slide | 2019-12-03 | Simon | Medium | [5 empty] | Closed |  | 2019-12-10 | Non-Stop | CG System
2 | App Discovery - CG System v1.3 | 9 | Logical View is more complicated than it needs to be - can be modeled without crossing lines. Logical views normally don't show transfer protocols (protocols could be changed without affecting logical view). There is no need for two diagrams to show same thing (process flow and protocols shown on slide 8 and 9). Between slides 8, 9, and 10, not sure what value-add is for slide 9. Suggest making one of these diagrams be "logical" (process flow, data flow) and another be "physical" (devices, servers, networks, protocols). | 2019-12-03 | Simon | Low | [5 empty] | Closed |  | 2019-12-10 | Non-Stop | CG System
3 | App Discovery - CG System v1.3 | 10 | Update to reflect location of Primary and DR Environments (See 12/9/19 comment below). Update to reflect the 3 SQL instances mentioned on Slide 12 and the server names. 12/9/19 (EEN): The production system is in Las Vegas while the DR is in Reno. Production server is named \APS1X and DR server is named \APS2X. | 2019-12-03 | Simon | High | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CG System
3b | All | 10a | Not having a decent physical model makes it difficult to account for all systems being referened in this doc (App Overview (5), BOM (14), Data Overview (12) and Interdependencies (20)) | 2019-12-03 | Simon | Medium | [5 empty] | Closed |  | 2019-12-10 | Non-Stop | All
4 | App Discovery - CG System v1.3 | 11 | Per process flow on slide 9, interfaces 3 & 4 Upstream interfaces not Downstream | 2019-12-03 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CG System
5 | App Discovery - CG System v1.3 | 14 | Type field is blank within Hardware/VM section. Update to physical servers 12/9/19 (EEN): Physical Servers are utilized | 2019-12-03 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CG System
6 | App Discovery - CG System v1.3 | 14 | Add missing Software? (SQL Server DB, Terminal Emulator/ Pathsend, Cohesity, MOMI, Telemetry, Idera). | 2019-12-03 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CG System
7 | App Discovery - CG System v1.3 | 14 | Add Dev tools (e.g., Bitbucket, Coverity, SonarQube, COBOL, SCOBOL) and Test tools (QAComplete, TestComplete) be listed in BOM? | 2019-12-03 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CG System
8 | App Discovery - CG System v1.3 | 14 | Apache Gateway and software are missing from BOM. | 2019-12-03 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CG System
9 | App Discovery - CG System v1.3 | 16 | "#5 Environments" Doesn't match what is listed on BOM (slide 14). The Physical View (slide 10) should account for all environments. | 2019-12-03 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CG System
10 | App Discovery - CG System v1.3 | 10 | "#10 Storage Type" are external enclosures, shouldn't these be listed on BOM (Slide 14)? | 2019-12-03 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CG System
11 | App Discovery - CG System v1.3 | 20 | Backup Methodology - Need to fix hyperlink for Data Overview ("Data Overv" portion links to correct slide but "iew" links to page 3). | 2019-12-03 | Simon | Low | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CG System
12 | App Discovery - CG System v1.3 | 20 | Application Instances: data inconsistent with data on BOM (14), Physical View (10). | 2019-12-03 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CG System
13 | App Discovery - CG System v1.3 | 20 | Database Instances: data inconsistent with data on BOM (14), Physical View (10), and Data Overview (12). | 2019-12-03 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CG System
14 | All HPE NS Systems | 22 (24 for Tandem Legacy) | The target host environment on slide 5 indicates "Azure Gov Internal" but the recommended Option 1 seems to indicate otherwise. 12/10/19 (KRG): Slide 5 represents the As-Is information that was provided to IBM team when SoW was initiated. | 2019-12-04 | Simon | Low | [5 empty] | closed |  | 2019-12-10 | Non-Stop
15 | All HPE NS Systems | 22 | At the top of the slide there is a statement "IBM recommends leveraging an Event Fabric Microservices Architecture..." but it is not clear which option would leverage this archtecture. Assuming it is not recommended Option 1, are there two recommended Options? | 2019-12-03 | Simon | Repeat | [5 empty] | Closed |  | 2019-12-10 | Non-Stop
16 | All HPE NS Systems | 22 | More clarity is needed in the description of Option 2. (Is this the option for the Event Fabric Microservices Architecture?) | 2019-12-03 | Simon | Repeat | [5 empty] | Closed |  | 2019-12-10 | Non-Stop
17 | All HPE NS Systems | 22 | Missing key data for evaluatiing these options - no cost figures (one time, re-occurring). Only Option 2 hints at durations. | 2019-12-03 | Simon | Repeat | [5 empty] | Closed |  | 2019-12-10 | Non-Stop
18 | All HPE NS Systems | 23 | Might want to indicate this pricing info is for Option 1a (assuming). | 2019-12-03 | Simon | Repeat | [5 empty] | Closed |  | 2019-12-10 | Non-Stop
19 | All HPE NS Systems | 23 | Quantities seem to indicate 4 sets of systems - would like to better understand how these map to Prod and DR/ Training environments. | 2019-12-03 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop
20 | All HPE NS Systems | 23 | Migration approach appears to be based on Option 1 - if so, please indicate so. | 2019-12-03 | Simon | Medium | [5 empty] | Defer to Design |  | 2019-12-10 | Non-Stop
21 | All HPE NS Systems | 25 | Wave plan shows application groupings but its not clear if waves must be completed sequentially or if they can run in parallel. Please clarify. | 2019-12-03 | Simon | Repeat | [5 empty] | Closed |  | 2019-12-10 | Non-Stop
22 | All HPE NS Systems | 26 | Migration approach appears to be based on Option 1 - if so, please indicate so. | 2019-12-03 | Simon | Repeat | [5 empty] | Closed |  | 2019-12-10 | Non-Stop
23 | All HPE NS Systems | 30 | Risk #1, 2, & 3 are tied to Option 1, and should be noted such. | 2019-12-03 | Simon | Low | [5 empty] | Defer to Design |  | 2019-12-10 | Non-Stop
24 | All HPE NS Systems | 30 | Risk #4 has a typo "rick" of failure. | 2019-12-03 | Simon | Low | [5 empty] | Defer to Design |  | 2019-12-10 | Non-Stop
25 | App Discovery - CG System v1.3 | 32 | Suggested Acros to add: BFF, DSI, RDF, vNS, NSK, SVN, SRE, CSR | 2019-12-03 | Simon | Low | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CG System
26a | App Discovery - CRIPS v1.3 | 5 | Assessment at a Glance #2 - states "…to complete within a year a year." Clarify meaning | 2019-12-10 | K. Guymon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CRIPS
26b | App Discovery - CRIPS v1.3 | 8 | Missing Interface Output to Tandem Missing Interface Input from External Systems - Disco Missing Interface Input from External Systems - POP Master Schedule Missing Manual Feed from ACTS, Firing Order | 2019-12-10 | K. Guymon | High | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CRIPS
26b | App Discovery - CRIPS v1.3 | 8 | Interface from CRIP to PICES should be confirmed. I believe this flow is CRIPS --> IBM Legacy --> PICES CRIPS --> Tandem --> PICES rather than a direct interface between the apps | 2019-12-10 | K. Guymon | High | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CRIPS
26 | App Discovery - CRIPS v1.3 | 8 | I suspect there is a error in process step #1 (Legacy Printing - sb Legacy Publishing) | 2019-12-04 | Simon | High | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CRIPS
27a | App Discovery - CRIPS v1.3 | 9 | APS1X HPE NonStop is not an Application Name. What is the name of the application or is the diagram simply representing a data store? | 2019-12-10 | K. Guymon | High | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CRIPS
27 | App Discovery - CRIPS v1.3 | 9 | This slide has all the same info as slide 9, with a little more beef. Would recommend ditching slide 8. | 2019-12-04 | Simon | n/a | [5 empty] | Closed |  | 2019-12-10 | Non-Stop | CRIPS
28 | App Discovery - CRIPS v1.3 | 9 | Karrie's Enhanced System-of-Systems diagram (showing business data dataflows) should be consulted for more possible interfaces with CRIPS not identified in this discovery doc. | 2019-12-04 | Simon | n/a | [5 empty] | Closed |  | 2019-12-10 | Non-Stop | CRIPS
29 | App Discovery - CRIPS v1.3 | 10 | Diagram on Slide 8 and Slide 9 do not match. | 2019-12-04 | Simon | High | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CRIPS
30 | App Discovery - CRIPS v1.3 | 11 | Resolve Type: Based on process flow on slide 9 CDG User (source) is not downstream (type) to CRIPS. | 2019-12-04 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CRIPS
31 | App Discovery - CRIPS v1.3 | 12 | #1 shows there are 3 NS SQL Instances, this is incorrect per Earl no SQL DB used by CG Systems? | 2019-12-04 | Simon | High | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CRIPS
32 | App Discovery - CRIPS v1.3 | 12 | This slide indicates a data replication flow to ADATA server, which doesn't appear on either the Logical or Physical views | 2019-12-04 | Simon | High | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CRIPS
33 | App Discovery - CRIPS v1.3 | 14 | The BOM calls out two databases which doesn't tie to # of instances noted in Slide 12. Also, why were the application systems not referenced in the Physcial view? | 2019-12-04 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CRIPS
34 | App Discovery - CRIPS v1.3 & MDPI | 14 | Apache Gateway and software are missing from BOM. 12/9/19 (EEN): CRIPS does not use Apache Gateway | 2019-12-04 | Simon | Medium | [5 empty] | Closed |  | 2019-12-10 | Non-Stop | CRIPS
35 | App Discovery - CRIPS v1.3 | 15 | Environments mentioned on this slide do not match with environments mentioned on slide 14 | 2019-12-04 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | CRIPS
36 | App Discovery - CRIPS v1.3 | 22 | The target host environment on slide 5 indicates "Azure Gov Internal" but the recommended Option 1 of side 22 seems to indicate otherwise. 12/10/19 (KRG): Slide 5 represents the As-Is information that was provided to IBM team when SoW was initiated. | 2019-12-04 | Simon | Low | [5 empty] | Closed |  | 2019-12-10 | Non-Stop | CRIPS
37 | App Discovery - CRIPS v1.3 | 30 | Risk #4 indicates that Pices (Wave 3) might have to migrate with CRIPS (Wave 4) and Legacy Publishing (Wave 4) (per Slide 25). Need to better understand how this affects the Wave plan. | 2019-12-04 | Simon | Medium | [5 empty] | Defer to Design |  | 2019-12-10 | Non-Stop | CRIPS
38 | App Discovery - MDPI v1.3 | 9 | This slide has all the same info as slide 9, with a little more beef. Would recommend ditching slide 8. | 2019-12-04 | Simon | n/a | [5 empty] | Closed |  | 2019-12-10 | Non-Stop | MDPI
39 | App Discovery - MDPI v1.3 | 9 | CG Systems, CRIPS, and SES call out an Apache Gateway for Boeing Client access - This is inaccurate. 12/9/19 (EEN): Only the CG system and SES system have Boeing users that use the Apache Gateway to access the system. | 2019-12-04 | Simon | Medium | [5 empty] | Closed |  | 2019-12-10 | Non-Stop | MDPI
40 | App Discovery - MDPI v1.3 | 10 | The box drawn around all the applications described as "MDPI Environment" and includes: the HPE NS system, IBM Mainframe (Legacy Publishing) and PICES this is misleading since those are separate systems | 2019-12-04 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | MDPI
41 | App Discovery - MDPI v1.3 | 11 | According to the process flow on slide 9, I'm having difficulting in understanding how CDG User (source) is a downstream (type) to MDPI. | 2019-12-04 | Simon | Low | [5 empty] | Open |  | 2019-12-10 | Non-Stop | MDPI
42 | App Discovery - MDPI v1.3 | 12 | #1 shows there are 3 NS SQL Instances, this is incorrect per Earl no SQL DB used by CG Systems? | 2019-12-04 | Simon | High | [5 empty] | Open |  | 2019-12-10 | Non-Stop | MDPI
43 | App Discovery - MDPI v1.3 | 12 | This slide indicates a data replication flow to ADATA server, which doesn't appear on either the Logical or Physical views | 2019-12-04 | Simon | High | [5 empty] | Open |  | 2019-12-10 | Non-Stop | MDPI
44 | App Discovery - MDPI v1.3 | 14 | The BOM calls out two databases which doesn't tie to # of instances noted in Slide 12. Also, why were the application systems not referenced in the Physcial view? | 2019-12-04 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | MDPI
45 | App Discovery - MDPI v1.3 | 14 | Apache Gateway and software are missing from BOM. | 2019-12-04 | Simon | Repeat | [5 empty] | Closed |  | 2019-12-10 | Non-Stop | MDPI
46 | App Discovery - MDPI v1.3 | 15 | Environments mentioned on this slide do not match with environments mentioned on slide 14 | 2019-12-04 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | MDPI
47 | App Discovery - MDPI v1.3 | 30 | Risk #4 indicates that Pices (Wave 3) might have to migrate with MDPI (Wave 4) and Legacy Publishing (Wave 4) (per Slide 25). Need to better understand how this affects the Wave plan. | 2019-12-04 | Simon | Repeat | [5 empty] | Closed |  | 2019-12-10 | Non-Stop | MDPI
48 | App Discovery - SES v1.3 | 9 | This slide has all the same info as slide 9, with a little more beef. Would recommend ditching slide 8. | 2019-12-04 | Simon | n/a | [5 empty] | Closed |  | 2019-12-10 | Non-Stop | SES
49 | App Discovery - SES v1.3 | 10 | The box drawn around all the applications described as "SES Environment" and includes: the HPE NS system, IBM Mainframe (Legacy Publishing) and PICES this is misleading since those are separate systems | 2019-12-04 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | SES
50 | App Discovery - SES v1.3 | 11 | According to the process flow on slide 9, I'm having difficulting in understanding how CDG User (source) is a downstream (type) to SES. | 2019-12-04 | Simon | Low | [5 empty] | Open |  | 2019-12-10 | Non-Stop | SES
51 | App Discovery - SES v1.3 | 12 | #1 shows there are 3 MS SQL Instances, this is incorrect per Earl no SQL DB used by CG Systems? | 2019-12-04 | Simon | High | [5 empty] | Open |  | 2019-12-10 | Non-Stop | SES
52 | App Discovery - SES v1.3 | 12 | This slide indicates a data replication flow to ADATA server, which doesn't appear on either the Logical or Physical views | 2019-12-04 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | SES
53 | App Discovery - SES v1.3 | 14 | The BOM calls out two databases which doesn't tie to # of instances noted in Slide 12. Also, why were the application systems not referenced in the Physcial view? | 2019-12-04 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | SES
54 | App Discovery - SES v1.3 | 15 | Environments mentioned on this slide do not match with environments mentioned on slide 14 | 2019-12-04 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | SES
55 | App Discovery - SES v1.3 | 30 | Risk #4 indicates that Pices (Wave 3) might have to migrate with SES (Wave 4) and Legacy Publishing (Wave 4) (per Slide 25). Need to better understand how this affects the Wave plan. | 2019-12-04 | Simon | Repeat | [5 empty] | Closed |  | 2019-12-10 | Non-Stop | SES
56 | App Discovery- Tamdem Legacy v1.3 | 8,9,10,11 | The techniques used to describe the Logical/ Contextual views and the physical views are unfortunately intermingled, causing more confusion than clarity. Logical/ Contextual views should be fairly stable and rarely need changing if the underlying infrastructure changes. Logical views usually change when the Business functionality changes. Physical views are generally more volitile due to changes in technology. Physical views should call out specific environment configurations and often times show IP addresses, host names for application and database systems, site locations, physical devices/ hardware icons, firewalls, load balancers, protocols, etc. | 2019-12-04 | Simon | Medium | [5 empty] | Defer to Design |  | 2019-12-10 | Non-Stop | Tandem Legacy
57 | App Discovery- Tamdem Legacy v1.3 | 9 | Slide 9 is a good attempt at a logical process view. Replace hardware icons with application boxes, replace protocols with business data, and you are closer to a logical view. | 2019-12-04 | Simon | Medium | [5 empty] | Closed |  | 2019-12-10 | Non-Stop | Tandem Legacy
58 | App Discovery- Tamdem Legacy v1.3 | 9 | CG Systems, CRIPS, and SES call out an Apache Gateway for Boeing Client access - This is inaccurate. 12/9/19 (EEN): Only the CG system and SES system have Boeing users that use the Apache Gateway to access the system. | 2019-12-04 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | Tandem Legacy
59 | App Discovery- Tamdem Legacy v1.3 | 11 | Slide 11 is a good attempt at a logical/ contextual view. | 2019-12-04 | Simon | N/A | [5 empty] | Closed |  | 2019-12-10 | Non-Stop | Tandem Legacy
60 | App Discovery- Tamdem Legacy v1.3 | 10 | Slide 10, as written, is redundant with slide 9. If meant to be a phyical view, then there should be a physical view for each of the environments (e.g., PROD, Training/DR) with hosted sites identified, application and database systems identified (host name, IP, FQDN) | 2019-12-04 | Simon | High | [5 empty] | Open |  | 2019-12-10 | Non-Stop | Tandem Legacy
61 | App Discovery- Tamdem Legacy v1.3 | 14 | If there are 3 NS SQL Instances, why weren't any of these called out on the physical view (slide 10)? | 2019-12-04 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | Tandem Legacy
62 | App Discovery- Tamdem Legacy v1.3 | 14 | This slide indicates a data replication flow to ADATA server, which doesn't appear on either the Logical or Physical views | 2019-12-04 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | Tandem Legacy
63 | App Discovery- Tamdem Legacy v1.3 | 16 | The BOM calls out two databases which doesn't tie to # of instances noted in Slide 14. Also, why were the application systems not referenced in the Physcial view? | 2019-12-04 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | Tandem Legacy
64 | App Discovery- Tamdem Legacy v1.3 | 18 | Environments mentioned on this slide do not match with environments mentioned on slide 16. | 2019-12-04 | Simon | Medium | [5 empty] | Open |  | 2019-12-10 | Non-Stop | Tandem Legacy
65 | App Discovery- Tamdem Legacy v1.3 | 30 | Risk #4 indicates that Pices (Wave 3) might have to migrate with Tandem Legacy (Wave 4) and Legacy Publishing (Wave 4) (per Slide 27). Need to better understand how this affects the Wave plan. | 2019-12-04 | Simon | Repeat | [5 empty] | Closed |  | 2019-12-10 | Non-Stop | Tandem Legacy
66 | All Deliverables | Overall | Options Analysis is too generic. It lacks sufficient details that would enable understanding of the options. missing clear enumeration of Technical Proposals, impact to ecosystem, costs, duration, and sufficient comparison between options. | 2019-12-03 | K. Guymon | High | [5 empty] | Defer to Design |  | 2019-12-10 | Non-Stop | All
67 | All Deliverables | Overall | Wave Plan (Phasing) needs to be aligned with Options and any Event Fabric proposals | 2019-12-03 | K. Guymon | High | [5 empty] | Defer to Design |  | 2019-12-10 | Non-Stop | All
68 | All Deliverables | Overall | Technical Proposal / Options need to provide clear picture of proposal (Options) for applications; including targeted environment, migration strategy, migration complexity. Improve Technical View /Clarity – Ecosystem / System of Systems with relationship to Event Fabric and the in-scope application. | 2019-12-03 | K. Guymon | High | [5 empty] | Defer to Design |  | 2019-12-10 | Non-Stop | All
69 | All Deliverables | Usually 12 | Special Data Handling needs to be updated based on InfoTypeByApp data that was provided in Nov (https://collab2.web.boeing.com/sites/OEIAHRestrictedAcces/CDG/Shared Documents/IBM POC/1 - Applications Working Folders/Misc/InfoTypeByApp.xlsx) | 2019-12-10 | K. Guymon | High | [5 empty] | Open |  | 2019-12-10 | Non-Stop | All
70 | App Discovery - CG System v1.3 | 22 | Option #2 - Is worded as a question rather than a proposal. Option is not clearly defined | 2019-12-10 | K. Guymon | High | [5 empty] | Defer to Design |  | 2019-12-10 | Non-Stop | CG System
71 | All NSK Deliverables | Risk Slide (Usually 30) | Risk #3: Kernel changes needs to much more clearly defined. * Why Required * What will change * Support Impact * Upgrade Impact * Security Considerations | 2019-12-10 | K. Guymon | High | [5 empty] | Defer to Design |  | 2019-12-10 | Non-Stop
72 | All NSK Deliverables | Risk Slide (Usually 30) | Risk #1: Consequence of Risk is shown as a Low (2), however without the vNS the entire Option / Recommendation will not work. Therefore Consequence seems more like High (5) | 2019-12-03 | K. Guymon | Medium | [5 empty] | Defer to Design |  | 2019-12-10 | Non-Stop
73 | All NSK Deliverables | Risk Slide (Usually 30) | Any Kernal changes for vNS has already been made by HP. IBM will not need to modify the HP Non-Stop OS. In our POC testing we didn't see anything that indicated a physical Non-Stop dependancy. Getting our code to build on vNS only required minor changes in the options passed to the linker during compilation. | 2019-12-04 | N. Bartlett | High | [5 empty] | Defer to Design |  | 2019-12-10 | Non-Stop
74 | All NSK Deliverables | Risk Slide (Usually 30) | Risk #4: Spelling error (Rick vs Risk) | 2019-12-03 | K. Guymon | Low | [5 empty] | Defer to Design |  | 2019-12-10 | Non-Stop
75 | All NSK Deliverables | Risk Slide (Usually 30) | Risk #4: Risk basically stating that tight Coupling = Must migrate simultaneously. The Risk needs to be clarified…are they really required to migrate simulatenously? What happens (Impact) if they do not migrate simulteanously? Additionally, mitigation is weak and doesn't appear to address requirement (simultaneous migration). | 2019-12-03 | K. Guymon | High | [5 empty] | Defer to Design |  | 2019-12-10 | Non-Stop
Note on G2: High : Major Flaw or Omission Middle: Error that impacts understanding, execution Low : Grammatical or context error that does not hamper understanding
Note on M2: Open Pending Closed Cancel

## Sheet1
Status Pick List
Open
Need to Discuss
Ready for Review
Closed
Defer to Design

## PivotBySeverityAndStatus
Count of Item # | Column Labels
Row Labels | Open | Defer to Design | Closed | Grand Total
High | 13 | 7 |  | 20
Medium | 27 | 4 | 5 | 36
Low | 5 | 3 | 3 | 11
Repeat |  |  | 10 | 10
n/a |  |  | 5 | 5
Grand Total | 45 | 14 | 23 | 82